## Slide 1
Scaled Agile Overview
Prepared by:
Ritesh Mandlik

## Slide 2: Agenda
Brief Overview
Example of Scaled Agile
PSI Planning
  Relative Sizing
  Estimation Board
  Team determines Capacity/Commitments
  PSI Plan
  Team Train Interaction & Dependencies
  Agile Hierarchy

## Slide 3: Brief Overview
The goal of scaled agile is frequent delivery of valuable, working and fully tested increments of solution.

## Slide 4: Example of Scaled Agile Methodology

## Slide 5: PSI Planning
PSI Planning
    Planning event scheduled few days before PSI
    Relative sizing of stories (Estimation Board)
    Team determines Capacity and Commitment (Data Sheet; PSI Plan)
      Use Historical Data
      Do Not Overcommit
      Fist of Five
    Team commits to deliverables at PSI level
    Team level grooming and stand-up
    Team level retrospectives

## Slide 6: First Day in PSI Planning
Welcome
    Spot Light Topic
Release Vision
It is review of Objectives by team
what is being asked for and the need it will meet.

## Slide 7: Second Day in PSI Planning
Planning
Collaborating (Scrum of Scrums)
PSI Level Commitment by Team

## Slide 8: Relative Sizing
All team members participate in defining the size of the story.
Rally provides a tool (Estimation Board) to enable this activity.

## Slide 9: Estimation Board

## Slide 10: Team Determines Capacity/Commitments
First step of planning is to review team member capacity
Team Capacity Calculation

## Slide 11: Team Determines Capacity/Commitments
Capacity Allocation
  Second step is for team to agree on how they will allocate their known capacity
    Example:
      Team A has 500 hours of capacity in Sprint 36-1
      User Stories= 70% (approximately 70 points)
      Defects=10%
      Grooming=15%
      Other?= 5%

## Slide 12: Team Determines Capacity/Commitments
User Story Allocation considering Capacity
    Third step is to allocate stories to sprints, until Capacity is reached.
      Utilize the PSI Plan board inside Rally
      After each sprint is populated, team takes final “vote” using Fist of Five.
        What is Fist of Five:
        ensures alignment across Team
        ALL team members are required to participate
        Confidence of 4 or above by all team members is required for commitment.

## Slide 13: PSI Plan

## Slide 14: Planning Completion Activity
PO Report Out
Objectives Slide
    What’s IN
    What’s OUT
    Dependencies
    Risks
    DO - SAY ratio review for prior PSI (begins with Current PSI)%
        Example:
        Said we would do 20 stories
        Did 15 stories
        75% Do – Say

## Slide 15: Team/Train Interactions & Dependencies

## Slide 16: Agile Structure

## Slide 17
Thank you!